## 10-Week Plan
Week | Milestones | Activities | Expected Outcomes
1 and 2 | Identify Potential Brokerages, Evaluate Brokerage Services and Fees, Initial Contact and Information Gathering | Research brokerage firms in Dubai, Compare services, fees, and reviews, Contact brokerages for detailed information. | List of potential brokerages, Comparative analysis, Shortlist for evaluation.
3 | Select the Preferred Brokerage Firm, Schedule In-Person Meetings | Review information and finalize a brokerage, Plan a Dubai trip, Schedule meetings with selected firms. | Selected brokerage firm, Meetings arranged to finalize account setup.
4 | Open the Brokerage Account, Complete Necessary Documentation, Initial Funding and Account Activation | Attend meetings and complete required forms, Submit legal documents, Transfer funds to activate the account. | Operational brokerage account, Full compliance with requirements.
4 | Purchase Low-Risk Stocks and ETFs, Analyze Transaction Costs and Commissions, Document Initial Investment Strategy | Execute stock/ETF purchases, Track and document all costs, Develop a basic investment strategy. | Portfolio of low-risk ETFs, Cost analysis report, Refined investment strategy.
5 | Outline Sales Pitch Structure, Draft Content for Sales Pitch, Design and Format the Document | Define key sections for the pitch, Write persuasive content, Add visuals and finalize the design. | Professional sales pitch document ready for use.
5 | Refine Investment Criteria and Processes, Establish Risk Management Protocols, Prepare SOPs | Develop asset selection criteria, Define risk assessment methods, Document operational processes for consistency. | Detailed investment strategies, Risk management framework, SOPs.
6 | Estimate Startup and Operational Costs, Develop Financial Projections, Determine Pricing and Fee Structures | Calculate setup and operational costs, Create financial models, Finalize 2% management and 20% performance fees. | Budget and financial projections, Transparent pricing structure.
6 | Develop Marketing Materials, Plan Client Outreach Strategy, Set Up Digital Presence | Design brochures and content, Identify target clients, Create a website and social media profiles. | Marketing materials, Client outreach plan, Established digital presence.
7 | Finalize Sales Pitch and Marketing Strategy, Initiate Team Recruitment Plans, Conduct a Soft Launch | Refine sales pitch and marketing, Draft job descriptions for key roles, Present services to select clients for feedback. | Polished sales pitch, Recruitment roadmap, Feedback from initial clients.

## Post-Plan Activities
Focus Area | Description
Team Recruitment and Training | Hire and train professionals for analysis, portfolio management, and compliance.
Client Acquisition and Management | Expand the client base, implement a CRM system, and maintain consistent performance reporting.
Asset Diversification | Gradually introduce fixed income and real estate assets based on client demand and market trends.
Regulatory Compliance | Stay updated on regulations and ensure compliance with Dubai’s financial laws.
Technology and Security | Invest in secure trading platforms, portfolio management software, and cybersecurity.