## Slide 1
PROJECT
RESOURCE
MANAGEMENT
PMP PREPARATION COURSE

## Slide 2
Project Resource Management includes the processes to identify, acquire, and manage the resources needed for the successful completion of the project.
1
2
3
Plan Resource Management
It defines how to estimate, acquire, manage, and utilize physical and team resources.
Estimate Activity Resources
estimating the type and quantities of resources necessary to perform project work
Acquire Resources
Obtaining human and physical resources necessary to complete project work.

## Slide 3
Resource include physical resources as well as human resources.
6
Develop Team
The process of improving competencies, interactions & team environment to enhance performance.
Manage Team
Tracking team member performance, providing feedback, resolving issues
Control Resources
Ensuring that the physical resources are available as planned, as well as monitoring the planned versus actual use of resources,
4
5

## Slide 4
TAILORING CONSIDERATIONS
01
02
03
04
DIVERSITY
PHYSICAL LOCATION
INDUSTRY SPECIFIC
RESOURCES
TEAM MGMT.
05
LIFE CYCLE
APPROACHES
What is diversity background of the team?
What is physical location of team members and physical resources?
What special resources are needed in the industry?
How is team development managed for the project?
What Life Cycle
Approaches will be used on the project?

## Slide 5
PLAN
RESOURCE MANAGEMENT
The process of defining
How to estimate,
Acquire, manage, and use team and physical resources.
INPUTS
1. Project charter
2. Project management plan
3. Project documents
Project schedule
Requirements documentation
Risk register  Stakeholder register
3. EEF 4. OPA
TOOLS & TECHNIQUES
1. Data representation
 Hierarchical charts
 Responsibility assignment matrix
 Text-oriented formats
2. Organizational theory
3. Expert judgment & Meetings
OUTPUTS
Resource management plan
Team charter
Project documents updates

## Slide 6
Data representation by using charts.
Various formats exist to document and
Communicate team member roles and
Responsibilities. Most fall into hierarchical, matrix, or text oriented formats.
DATA REPRESENTATION

## Slide 7
DATA REPRESENTATION-CHARTS
1- HIERARCHICAL - ORGANIZATIONAL CHART
2- ASSIGNMENT MATRIX
A- Responsibility Assignment
Matrix - RAM
(who will do what?)
B- RACI Matrix
(Responsible - Accountable –
Consult - Inform)
RACI CHART | Person |  |  |  | 
Activity | Ann | Ben | Carlos | Dina | Ed
Create charter | A | R | I | I | I
Collect requirements | I | A | R | C | C
Submit change request | I | A | R | R | C
Develop test plan | A | C | I | I | R
Deliverable |  | People | Project manager | Task leader | Staffer A | Group director | Purchasing
WBS code | Title |  |  |  |  |  | 
2.3- | Questionnaire design |  | A | S.A | P |  | 
3.3- | Respondents |  |  | P |  |  | 
4.4- | Pretest |  |  | P | S |  | 
6.5- | Final questionnaire printing |  | A | P |  | A | A

## Slide 8
Describes specific role or job skills and competencies. May include details on languages, technology, or other information necessary to complete the role successfully
3- TEXT-ORIENTED FORMAT
DATA REPRESENTATION-CHARTS
ROLES AND RESPONSIBILITIES
Project Title:ــــــــــــــــــــــــــــــــ
Date Prepared: ــــــــــــــــــــــــــــــــ
Resource Role Description:
Provides the role or job title and a brief description of the role.
Authority:
Defines the decision-making limits for each role. Examples include alternative selection, conflict management, prioritizing, rewarding and penalizing, etc. Also indicates reporting structure.
Responsibility:
Defines the activities that the role carries out and the nature of the contribution to the final product, service, or result. Examples include job duties, processes involved, and hand-offs to other people.
Qualifications:
Describes any prerequisites, experience, licenses, seniority levels, or other qualifications necessary to fulfill the role
Competencies:

## Slide 9
ORGANIZATION
THEORIES

## Slide 10
ORGANIZATION THEORIES
MASLOW’S HIERARCHY OF NEEDS
People have needs, and until the lower ones are satisfied they won't even begin to think about the higher ones.
Morality,
creativity ,
Spontaneity,
problem solving,
lack of prejudice,
acceptance of facts
Self-esteem, confidence,
achievement respect of others,
respect by others
Friendship,family,sexual intimacy
Security of : body, employment, resources,
morality, the family, health, property
Breathing,food,water,sex,sleep,homeostasis,excretion
Self-actualization
Esteem
Love/belonging
Safety
Physiological

## Slide 11
ORGANIZATION THEORIES
HERZBERG'S THEORY OF MOTIVATION
Hygiene agents
1- Job security
2- Salary
3- Acceptable working conditions
4- Relationships
Motivating agents
1- Opportunity
2- Responsibility
3- Appreciation
4- Recognition
5- Education

## Slide 12
THEORY X & THEORY Y
THEORY X
Management assumed employees are lazy and hate work.
THEORY Y
Employees enjoy their physical and mental work.
ORGANIZATION THEORIES